## Ringkasan
Estimasi Mandays Pengembangan -- SRS v2.0
Company Digital Office System -- 22 Modul, 13 Role, 3 Portal (External Website, Client Portal, Internal Portal)
PT RTN ¦ Estimasi bila dikerjakan tim developer tanpa bantuan AI ¦ Superseded: estimasi kontrak-payung sebelumnya (114 md) kini bagian dari Fase 1
RINGKASAN ANGKA
Total Estimasi Mandays (termasuk overhead PM) | md | 462
Jumlah Task/Deliverable Teridentifikasi | task | 59
Estimasi Durasi Kalender (tim inti ~9-10 orang, fase overlap wajar) |  | 8-9 bulan
Estimasi Durasi Kalender (tanpa overlap, fase strict berurutan) | minggu | 28
KOMPOSISI TIM REKOMENDASI
Role | Alokasi | Total Mandays | Catatan Peran
Project Manager (Delivery) | 100% sepanjang proyek (~9 bulan) | 42 | Koordinasi, status report mingguan, change request, komunikasi stakeholder
Tech Lead / Senior Developer | 100% sepanjang proyek | 109 | Arsitektur, modul Finance/Payroll, rekonsiliasi dgn sistem existing, review kode
Backend Developer | 100%, terkonsentrasi di Fase 1 | 36 | Bisa merangkap Fullstack Developer di fase lain untuk efisiensi biaya
Fullstack Developer (Livewire) | 2-3 orang x 100% | 170 | Beban terbesar (170 md) -- modul UI/Livewire tersebar di semua fase
Frontend/Web Developer | Part-time/project-based (~1 bulan) | 18 | Hanya intensif di Fase 4 (External Website)
UI/UX Designer | Part-time (~3 minggu, terutama Fase 0) | 15 | Wireframe/mockup seluruh layar baru
QA / Tester | 1-2 orang, penuh mulai Fase 5 | 38 | Disarankan terlibat sejak Fase 1 untuk smoke test incremental
Business Analyst | Part-time sepanjang proyek | 22 | Padat di Fase 0 (requirement) & Fase 6 (dokumentasi/training)
DevOps / Infrastructure | Part-time, terutama Fase 6 | 12 | Infrastruktur, CI/CD, deployment, monitoring
TOTAL |  | 462
CATATAN & ASUMSI PENTING
• Estimasi ini SUPERSEDE estimasi sebelumnya (114 md, khusus modul kontrak payung/spesifik) -- scope SRS v2.0 jauh lebih besar (22 modul, 13 role, 3 portal) dan kini mencakup pekerjaan itu di dalam Fase 1.
• 4 TEMUAN KRITIS dari analisa gap (lihat dok 'perbandingan-srs-v2-vs-sistem-existing') BELUM terjawab saat estimasi ini dibuat, dan mempengaruhi akurasi Fase 1 & Fase 2: (1) role 'Project Controller' yang sudah dibangun vs 'Project Control' di SRS beda fungsi; (2) istilah kontrak spesifik/payung & alur Release Order tidak muncul eksplisit di SRS; (3) kebutuhan e-signature bersertifikat (PSrE/Peruri) vs in-house yang sudah dibangun; (4) hierarki data Unit (existing) vs Client/Lokasi (SRS). Rekomendasi: konfirmasi dulu sebelum kontrak ditandatangani -- lihat baris bercatatan di sheet 'Rincian Modul'.
• 1 manday = 1 orang bekerja 1 hari efektif (~7 jam), 5 hari kerja/minggu.
• Overhead Project Management dihitung otomatis 10% dari total mandays teknis (baris terakhir di 'Rincian Modul').
• Belum termasuk: lisensi/biaya hosting & infrastruktur cloud (tergantung pilihan provider), kontinjensi perubahan scope di tengah jalan, dan tarif harian (isi sendiri di sheet 'Rekap per Role').
• Modul yang sudah berjalan di sistem existing (Project Management, Purchasing & Material Tracking, KPI & Work Log, Auth dasar) diberi porsi mandays jauh lebih kecil karena tinggal penyesuaian, bukan dibangun dari nol.

## Rincian Modul
Rincian Modul & Estimasi Mandays per Fase (SRS v2.0)
No | Fase | Modul / Task | Role | Mandays | Catatan
1 | Fase 0 - Analisa & Desain | Analisa proses bisnis & functional spec 22 modul, 13 role, 3 portal | Business Analyst | 10
2 | Fase 0 - Analisa & Desain | Desain ERD lengkap (seluruh modul, termasuk integrasi dgn skema existing) | Tech Lead / Senior Developer | 8
3 | Fase 0 - Analisa & Desain | Desain arsitektur 3 portal (shared authentication, isolasi data eksternal/internal) | Tech Lead / Senior Developer | 6
4 | Fase 0 - Analisa & Desain | Wireframe/mockup: login, dashboard (min 7 role), external website, client portal, form BOQ/Penawaran, invoice, kasbon, admin user management | UI/UX Designer | 15 | Wajib dilampirkan di proposal vendor sesuai SRS bab 7.1
5 | Fase 0 - Analisa & Desain | Tech stack justification & dokumen rencana proyek | Tech Lead / Senior Developer | 2
6 | Fase 0 - Analisa & Desain | Review & sign-off desain dengan stakeholder | Business Analyst | 1
7 | Fase 0 - Analisa & Desain | Review & sign-off desain dengan stakeholder | Tech Lead / Senior Developer | 1
8 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Role & permission sesuai 13 role SRS (pemisahan Project Control vs Project Controller, Cost Control, Lead Technician, Admin, dll) | Backend Developer | 4 | Perlu klarifikasi dulu -- lihat temuan 3.1 di analisa gap
9 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Penyesuaian Authentication & User Management (audit log login, bulk import CSV/Excel) | Backend Developer | 6
10 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Master Sparepart/Material terstruktur per Tipe Pompa + Engine + Serial Number | Backend Developer | 5
11 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Master Unit Pompa (Aset Klien): serial number, riwayat service, kondisi terakhir | Fullstack Developer (Livewire) | 6
12 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Penyesuaian Master Client & Vendor (field tambahan) | Backend Developer | 3
13 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Rekonsiliasi hierarki data: Unit (existing) vs Client/Lokasi (SRS) + migrasi data | Tech Lead / Senior Developer | 5 | Lihat temuan 3.4 di analisa gap
14 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Rekonsiliasi alur Kontrak Payung/RO/CustomerQuotation (existing) vs alur BOQ & Penawaran / BAPP RO (SRS 5.1) | Tech Lead / Senior Developer | 5 | Lihat temuan 3.2 -- keputusan arsitektur penting, sebaiknya dikonfirmasi dulu
15 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Penyesuaian Project Management: hierarki Region->Client/Lokasi->Kontrak->Proyek->Activity/Checkpoint, 5 tipe proyek | Tech Lead / Senior Developer | 8
16 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Assignment & Scheduling 2-tahap (Lead Technician usul, PM/Project Control approve), request safetyman/admin lokasi | Fullstack Developer (Livewire) | 8
17 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Operasional Lapangan & Laporan Teknisi (Safety Talk/Toolbox log, jam kerja terstruktur, link Kasbon/Expense, Simlok/SIKA H-3) | Fullstack Developer (Livewire) | 10
18 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Document Management terstruktur (folder taxonomy, matriks akses, versioning, preview inline, bulk download zip) | Fullstack Developer (Livewire) | 14
19 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | BOQ & Penawaran Service & Maintenance (filter item per tipe pompa/engine/SN, approval PM/Direktur) | Tech Lead / Senior Developer | 10 | Berpotensi tumpang-tindih dgn modul existing -- lihat temuan 3.2
20 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Penyesuaian Purchasing & Material Tracking (reminder H-7) | Backend Developer | 4
21 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Admin Operasional (Admin Kantor: rekap, BAPP, BAL; Admin Purchase: surat jalan, gatepass) | Fullstack Developer (Livewire) | 10
22 | Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Penyesuaian KPI & Work Log | Backend Developer | 3
23 | Fase 2 - Keuangan & SDM | Finance & Accounting: Entry Voucher, Cash & Bank, General Ledger | Tech Lead / Senior Developer | 12 | Modul paling kompleks di seluruh SRS
24 | Fase 2 - Keuangan & SDM | Finance & Accounting: Accounts Payable, Accounts Receivable, Asset Management | Tech Lead / Senior Developer | 8
25 | Fase 2 - Keuangan & SDM | Finance & Accounting: Budgeting & Forecasting, Reporting & Analysis | Tech Lead / Senior Developer | 5
26 | Fase 2 - Keuangan & SDM | Invoice & Billing (nomor otomatis, PDF, partial payment, aging) | Fullstack Developer (Livewire) | 8
27 | Fase 2 - Keuangan & SDM | Kasbon/Cash Advance & Expense (approval 2 tahap, settlement) | Fullstack Developer (Livewire) | 8
28 | Fase 2 - Keuangan & SDM | Payroll (kalkulasi gaji, lembur, BPJS, PPh21, payslip, approval Direktur) | Tech Lead / Senior Developer | 12 | Perlu validasi aturan BPJS/PPh21 final perusahaan sebelum development
29 | Fase 2 - Keuangan & SDM | Cost Control (dashboard budget vs actual, alert threshold, tarik data lintas modul) | Fullstack Developer (Livewire) | 8
30 | Fase 2 - Keuangan & SDM | Absensi/Attendance umum (check-in/out kantor, izin/cuti/sakit/alfa, integrasi payroll) | Fullstack Developer (Livewire) | 8 | Terpisah dari Presensi GPS lapangan yang sudah ada (lihat temuan 3.4-ish, SRS 4.20)
31 | Fase 3 - Divisi 1 (Sales & Pengadaan Pompa Baru) | CRM & Sales Pipeline (leads, pipeline visual, log aktivitas, reminder, dashboard Marketing) | Fullstack Developer (Livewire) | 12
32 | Fase 3 - Divisi 1 (Sales & Pengadaan Pompa Baru) | Inventory Stok Pompa | Fullstack Developer (Livewire) | 4
33 | Fase 3 - Divisi 1 (Sales & Pengadaan Pompa Baru) | RFQ & BOQ Penjualan | Fullstack Developer (Livewire) | 6
34 | Fase 3 - Divisi 1 (Sales & Pengadaan Pompa Baru) | Penawaran Harga & Technical Data (approval, PDF, revisi) | Fullstack Developer (Livewire) | 8
35 | Fase 3 - Divisi 1 (Sales & Pengadaan Pompa Baru) | PO Masuk, BA Serah Terima, VDRL, Sales Order | Fullstack Developer (Livewire) | 10
36 | Fase 4 - External-Facing & Cross-Cutting | External Company Website (6 halaman, CMS, SEO, responsif) | Frontend/Web Developer | 18
37 | Fase 4 - External-Facing & Cross-Cutting | Client Portal (login, dashboard, progress real-time, dokumen, invoice read-only) | Fullstack Developer (Livewire) | 14
38 | Fase 4 - External-Facing & Cross-Cutting | SSO routing 3 portal (External/Client/Internal) | Backend Developer | 3
39 | Fase 4 - External-Facing & Cross-Cutting | Notification & Audit Trail (in-app + email, audit trail immutable) | Tech Lead / Senior Developer | 10
40 | Fase 4 - External-Facing & Cross-Cutting | Dashboard per Role (11 role tersisa: PM, Project Control, Cost Control, Finance, Lead Tech, Technician, Purchasing, Admin, Marketing, Sales Support, Client Portal) | Fullstack Developer (Livewire) | 16
41 | Fase 5 - QA & Integrasi | Penyusunan test case menyeluruh | QA / Tester | 8
42 | Fase 5 - QA & Integrasi | Functional testing seluruh modul (22 modul) | QA / Tester | 20
43 | Fase 5 - QA & Integrasi | Regression testing modul existing yang berubah | QA / Tester | 5
44 | Fase 5 - QA & Integrasi | Security testing (validasi upload, permission matrix, autentikasi) | QA / Tester | 5
45 | Fase 5 - QA & Integrasi | Integrasi lintas modul (Finance, Cost Control, Notification menarik data dari banyak modul) | Tech Lead / Senior Developer | 8
46 | Fase 5 - QA & Integrasi | Bug fixing | Backend Developer | 8
47 | Fase 5 - QA & Integrasi | Bug fixing | Fullstack Developer (Livewire) | 8
48 | Fase 5 - QA & Integrasi | UAT bersama user (iteratif, lintas 2 divisi + Finance + Direktur) | Fullstack Developer (Livewire) | 6
49 | Fase 5 - QA & Integrasi | Perbaikan hasil UAT | Fullstack Developer (Livewire) | 6
50 | Fase 6 - Deployment & Dokumentasi | Setup infrastruktur production (server, HTTPS/TLS, backup harian, monitoring) | DevOps / Infrastructure | 5
51 | Fase 6 - Deployment & Dokumentasi | CI/CD, staging environment, dokumentasi API (Swagger/OpenAPI) | DevOps / Infrastructure | 5
52 | Fase 6 - Deployment & Dokumentasi | Migration rehearsal + rollback plan (termasuk data existing) | Tech Lead / Senior Developer | 3
53 | Fase 6 - Deployment & Dokumentasi | Deployment ke production + monitoring pasca-rilis | DevOps / Infrastructure | 2
54 | Fase 6 - Deployment & Dokumentasi | Dokumentasi teknis (architecture docs, ERD final, API docs) | Tech Lead / Senior Developer | 3
55 | Fase 6 - Deployment & Dokumentasi | User manual untuk 13 role | Business Analyst | 6
56 | Fase 6 - Deployment & Dokumentasi | Panduan Administrator | Business Analyst | 2
57 | Fase 6 - Deployment & Dokumentasi | Training session untuk pengguna kunci | Business Analyst | 3
58 | Fase 6 - Deployment & Dokumentasi | Data migration plan (data existing ke skema baru) | Tech Lead / Senior Developer | 3
59 | Lintas Fase (Overhead) | Project Management & koordinasi (sprint planning, status report, change request, koordinasi stakeholder) | Project Manager (Delivery) | 42 | Dihitung otomatis: 10 persen dari total mandays teknis (baris 1-58)
|  | TOTAL |  | 462

## Rekap per Role
Rekap Mandays & Estimasi Biaya per Role
Isi kolom 'Tarif per Manday (Rp)' (sel kuning) sesuai standar rate internal perusahaan Anda.
Role | Total Mandays | Tarif per Manday (Rp) | Total Estimasi Biaya (Rp)
Project Manager (Delivery) | 42 | 0 | 0
Tech Lead / Senior Developer | 109 | 0 | 0
Backend Developer | 36 | 0 | 0
Fullstack Developer (Livewire) | 170 | 0 | 0
Frontend/Web Developer | 18 | 0 | 0
UI/UX Designer | 15 | 0 | 0
QA / Tester | 38 | 0 | 0
Business Analyst | 22 | 0 | 0
DevOps / Infrastructure | 12 | 0 | 0
TOTAL | 462 |  | 0
Catatan: Total Mandays ditarik otomatis (SUMIF) dari sheet 'Rincian Modul', termasuk baris overhead Project Management. Tarif per manday TIDAK diisi otomatis -- sesuaikan dengan standar gaji/vendor rate perusahaan.

## Timeline
Timeline Estimasi per Fase (SRS v2.0)
Asumsi tim inti: 1 PM + 1 Tech Lead + 1 Backend Dev + 2-3 Fullstack Dev + 1 QA (+ Web Dev, UI/UX, BA, DevOps paruh waktu)
Fase | Deskripsi Singkat | Role Terlibat | Mandays Fase | Estimasi Durasi (minggu)
Fase 0 - Analisa & Desain | Functional spec, ERD, arsitektur 3 portal, wireframe, sign-off | BA, Tech Lead, UI/UX Designer | 43 | 3
Fase 1 - Fondasi & Divisi 2 (Service & Maintenance) | Fondasi platform + rapikan Divisi 2 (Service & Maintenance) sesuai SRS, termasuk rekonsiliasi dgn sistem existing | Tech Lead, Backend Dev, Fullstack Dev | 101 | 5
Fase 2 - Keuangan & SDM | Finance & Accounting, Invoice, Kasbon/Expense, Payroll, Cost Control, Absensi umum | Tech Lead, Fullstack Dev | 69 | 4
Fase 3 - Divisi 1 (Sales & Pengadaan Pompa Baru) | Divisi 1: CRM, Sales Pipeline, Inventory, BOQ Penjualan, Sales Order | Fullstack Dev | 40 | 4
Fase 4 - External-Facing & Cross-Cutting | External Website, Client Portal, SSO 3 portal, Notification & Audit Trail, Dashboard per role | Web Dev, Fullstack Dev, Backend Dev, Tech Lead | 61 | 4
Fase 5 - QA & Integrasi | Test case, functional & regression & security testing, bug fixing, UAT | QA, Backend Dev, Fullstack Dev | 74 | 5
Fase 6 - Deployment & Dokumentasi | Infrastruktur produksi, deployment, dokumentasi, training | DevOps, Tech Lead, Business Analyst | 32 | 3
TOTAL (bila fase berurutan penuh, tanpa overlap) |  |  | 420 | 28
Catatan: total minggu di atas mengasumsikan fase berjalan strict berurutan (worst case), TIDAK termasuk mandays overhead Project Management (dihitung terpisah, lihat sheet Ringkasan). Dengan overlap wajar (mis. Fase 2 & 3 bisa mulai sebagian begitu fondasi Fase 1 selesai, QA berjalan incremental bukan hanya di Fase 5), durasi realistis untuk tim ~9-10 orang adalah 8-9 bulan kalender.